## Sheet1
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Group 2 | 2026-03-03 | Column naming conventions are inconsistent and do not meet production standards. | S1 | Group 2 | Logical | Standardized column names based on defined production naming conventions. | 2026-03-03 | Closed | Naming standardized; no inconsistencies remain.
2 | Group 2 | 2026-03-06 | Integration across multiple features exhibits stability issues. | S1 | Group 2 | Integration | Identified and resolved integration conflicts between dependent modules. | 2026-03-07 | Closed | Integration stabilized; no further issues observed.
3 | Group 2 | 2026-03-09 | UI toggle theme has color contrast issues affecting readability in light mode. | S2 | Group 2 | UI / UX | Updated color palette to meet accessibility (contrast) standards. | 2026-03-09 | Closed | Contrast improved; readability meets standards.
4 | Group 2 | 2026-03-12 | Graph rendering inconsistencies observed across department-level data visualizations. | S2 | Group 2 | Functional | Fixed data mapping and rendering logic for graphs. | 2026-03-13 | Closed | Rendering consistent across all departments.
5 | Group 2 | 2026-03-15 | Issues encountered while adding new pages to the dashboard. | S3 | Group 2 | Functional | Resolved errors in page creation workflow and routing logic. | 2026-03-15 | Closed | Page creation functioning as expected.
6 | Group 2 | 2026-03-18 | The Medevac Tracker exhibits data stability issues, resulting in inconsistent or unreliable data. | S3 | Group 2 | Data Integrity | Addressed data synchronization and integrity issues. | 2026-03-19 | Closed | Data stability achieved; outputs are reliable.
7 | Group 2 | 2026-03-21 | Issues identified in the caching mechanism. | S4 | Group 2 | Performance | Fixed cache invalidation logic to prevent stale data. | 2026-03-21 | Closed | Caching optimized; no inconsistencies observed.
8 | Group 2 | 2026-03-24 | Minor issues encountered during full end-to-end execution of the system. | S4 | Group 2 | System / E2E | Identified and resolved minor defects found during E2E testing. | 2026-03-25 | Closed | Issues resolved; end-to-end flow is stable.